## Jira Import
Task ID | Issue Type | Summary | Epic Link | Phase | Status | Priority | Story Points | Depends On | Affected Files | Description / Acceptance Criteria | Components | Labels
| Epic | Invite-based user onboarding (Platform / Tenant) |  |  | In Progress | Highest |  |  | database/schema.sql, services/config/**, admin-ui/** | Replace the temp-password POST /users flow with an invite-based onboarding path covering platform (superadmin) and tenant (admin) levels, widen roles to supervisor/agent, and add case-insensitive email uniqueness. Source: .sdlc/user-onboarding-hierarchy/03-tasks.md | config-service, admin-ui, database | onboarding invites rbac
T1 | Task | Widen users_role_check to include supervisor/agent and add users.team | Invite-based user onboarding (Platform / Tenant) | Phase 1: Schema | Done | High | 2 |  | database/schema.sql | psql -f database/schema.sql run twice in a row against a seeded dev DB both succeed with no error, and INSERT INTO users (..., role) VALUES (..., 'supervisor') succeeds while role='bogus' still fails the CHECK. | database | onboarding schema
T2 | Task | Drop the case-sensitive users_email_key constraint | Invite-based user onboarding (Platform / Tenant) | Phase 1: Schema | Done | High | 1 | T1 | database/schema.sql | Applying the file leaves \d users showing no users_email_key, and inserting two live rows differing only in case succeeds (proving the old constraint is gone) before the next step re-guards it. | database | onboarding schema
T3 | Task | Add guarded lower-casing email backfill with collision detection | Invite-based user onboarding (Platform / Tenant) | Phase 1: Schema | Done | High | 3 | T2 | database/schema.sql | A test seeding Bob@x.com and bob@x.com as live rows makes schema.sql raise the named exception and leaves the table unmodified (lesson 5), and a fixture with only one of them applies cleanly with the row lower-cased. | database | onboarding schema
T4 | Task | Add partial unique index users_email_lower_idx on lower(email) WHERE deleted_at IS NULL | Invite-based user onboarding (Platform / Tenant) | Phase 1: Schema | Done | High | 2 | T3 | database/schema.sql | Two soft-deleted rows sharing a lower-cased address are allowed, a second live row at that address is rejected, and re-running schema.sql is a no-op (CREATE UNIQUE INDEX IF NOT EXISTS). | database | onboarding schema
T5 | Task | Create user_invites table plus its two indexes | Invite-based user onboarding (Platform / Tenant) | Phase 1: Schema | Done | High | 3 | T4 | database/schema.sql | schema.sql applied twice is a no-op both times; two pending invites for the same email in the same tenant collide with UniqueViolationError; two pending invites for the same email in DIFFERENT tenants both insert successfully (lesson 3 — scope check). Indexes: user_invites_pending_email_idx scoped per-tenant via COALESCE(tenant_id, '00000...'), and user_invites_tenant_idx. | database | onboarding schema
T6 | Task | Split get_current_user into get_authenticated_user and a console-gated get_current_user | Invite-based user onboarding (Platform / Tenant) | Phase 2: Backend core (identity, permissions, tokens) | To Do | Highest | 3 | T1 | services/config/deps.py, services/config/routers/auth.py | Introduce CONSOLE_ROLES = frozenset({'superadmin','admin','viewer'}); switch routers/auth.py's /auth/me and /auth/change-password to Depends(get_authenticated_user). Done when: a supervisor and an agent JWT get 403 from GET /users, /provider-configs, /carriers, /calls, /audit-log, but 200/204 from /auth/me and /auth/change-password; a viewer JWT (including is_service_account=true, tenant_id=None) still gets 200 on those reads; unauthenticated GET /health, /auth/setup-status, POST /auth/login, POST /auth/bootstrap all still reach their handlers with no 401/403 from the gate; and a test enumerates every route in the app and asserts exactly two depend on get_authenticated_user. Scope this tripwire test to route enumeration driven off the shared deps module rather than a Config-app-only assumption, since Knowledge/DID/Campaigns import this same module (lesson 9). | config-service | onboarding rbac backend
T7 | Task | Add may_invite() privilege-escalation guard | Invite-based user onboarding (Platform / Tenant) | Phase 2: Backend core (identity, permissions, tokens) | To Do | Highest | 3 | T1 | services/config/invites.py (new) | Signature: may_invite(*, actor_role, actor_tenant_id, target_role, target_tenant_id) -> bool. Done when the privilege-escalation matrix test passes: tenant_admin->superadmin denied (AC2); tenant_admin->any role with tenant_id != actor's, including tenant_id=None, denied (AC3); tenant_admin->{tenant_admin,supervisor,agent,viewer} in own tenant allowed (AC4); superadmin->tenant_admin anywhere and ->superadmin allowed; supervisor/agent as actor denied for every target; and every role in users_role_check is explicitly classified as console or non-console by a companion assertion. | config-service | onboarding rbac backend
T8 | Task | Add _new_token() invite token generator (urlsafe + sha256) | Invite-based user onboarding (Platform / Tenant) | Phase 2: Backend core (identity, permissions, tokens) | To Do | High | 1 |  | services/config/invites.py | _new_token() = secrets.token_urlsafe(32) -> (raw, sha256_hex). Done when: a test asserts the raw token is >=43 chars, 1000 calls produce zero hash collisions, and the raw value never appears in any log record, response body or audit_log row produced elsewhere in the suite. | config-service | onboarding rbac backend
T9 | Task | Add create_invite, resend_invite, revoke_invite with tenant-blind conflict handling | Invite-based user onboarding (Platform / Tenant) | Phase 2: Backend core (identity, permissions, tokens) | To Do | Highest | 5 | T5, T7, T8 | services/config/invites.py | Each calls may_invite with the STORED row's role/tenant for resend/revoke, 404 first if the row is absent; plus the tenant-scoped conflict check (409 flat string for tenant_admin, tenant-naming 409 for super_admin) and the UniqueViolationError->409 mapping for a concurrent double-send. Done when: a tenant_admin inviting an email that exists in another tenant gets exactly {"detail": "this email cannot be invited"} with no tenant slug/name/id in the body, byte-identical to the response for an email with a pending invite in the actor's own tenant; the same request as super_admin names the tenant; and a tenant_admin resend/revoke of a Tenant B invite id, or of a superadmin invite, returns 403 (IDOR test, AC2/AC3 replayed against stored rows). create_invite returns the row and raw token only — email delivery is invoked by the router in Phase 3, not here. | config-service | onboarding rbac backend
T10 | Task | Add accept_invite() atomic three-step transaction | Invite-based user onboarding (Platform / Tenant) | Phase 2: Backend core (identity, permissions, tokens) | To Do | Highest | 5 | T5, T9, T11 | services/config/invites.py | Implements: classify row -> conditional UPDATE ... WHERE status='pending' AND expires_at > now() RETURNING * -> _insert_user -> set accepted_user_id -> write_audit; catching the users-table UniqueViolationError as EmailTaken WITHOUT burning the invite. Done when: two simultaneous accept_invite calls with the same token produce exactly one accepted row and one InviteUsed raised (asserted as distinct from expired/revoked), with exactly one row in users; a squatting scenario (Tenant A and Tenant B both holding a pending invite for the same email) has the second accept raise EmailTaken with a tenant-blind message and leave that invite still pending (resendable/revocable) rather than 500ing; and expired/revoked/already-accepted tokens each raise their own named exception, distinctly. | config-service | onboarding rbac backend
T11 | Task | Add team column to _insert_user() | Invite-based user onboarding (Platform / Tenant) | Phase 2: Backend core (identity, permissions, tokens) | To Do | Medium | 1 | T1 | services/config/users.py | Done when existing test_users.py cases pass unchanged (POST /users is untouched here — its removal is a Phase 3 task, once the invite path is reachable). NOTE: the email lower-casing in _insert_user and get_user_by_email originally scoped here MOVED INTO Phase 1 (T4's review fix) because users_email_lower_idx cannot ship without it — do not re-do it here. | config-service | onboarding rbac backend
T12 | Task | Add token_hash to the audit redaction set | Invite-based user onboarding (Platform / Tenant) | Phase 2: Backend core (identity, permissions, tokens) | To Do | High | 1 |  | services/config/audit.py | An accept/resend/revoke test inspects the written audit_log row and asserts token_hash is absent/redacted while entity_type/action/actor are present. | config-service | onboarding rbac backend
T13 | Task | Add InviteCreate / InviteAccept schemas and widen UserUpdate role Literal | Invite-based user onboarding (Platform / Tenant) | Phase 2: Backend core (identity, permissions, tokens) | To Do | High | 2 | T1 | services/config/schemas.py | InviteAccept carries password: str = Field(min_length=8). Done when: InviteAccept(password="short") raises a validation error and password="12345678" does not; UserUpdate(role="supervisor") validates. | config-service | onboarding rbac backend
T14 | Task | Widen Role Literal to include supervisor and agent | Invite-based user onboarding (Platform / Tenant) | Phase 2: Backend core (identity, permissions, tokens) | To Do | Medium | 1 | T1 | services/config/auth.py:23 | Widen Role = Literal["superadmin","admin","viewer"] to include "supervisor","agent". Done when: mypy/type-check on services/config passes and a JWT payload carrying role="supervisor" type-checks as Role (no runtime behavior change; this closes the stale-Literal drift the design flagged as deprioritized). | config-service | onboarding rbac backend
T15 | Task | Add send_invite_email() via stdlib smtplib with secret-ref SMTP password | Invite-based user onboarding (Platform / Tenant) | Phase 3: API, email delivery and cutover | To Do | High | 3 |  | services/config/email.py (new), docs/setup.md | Reads SMTP_HOST/PORT/USER/FROM and SMTP_PASSWORD_REF via the repo's existing secret-ref resolver (libs/config_sdk/secrets.py), and documents the new env vars alongside INVITE_BASE_URL. Done when: with SMTP mocked to raise, calling send_invite_email() directly raises/returns a failure the caller can catch without crashing; with SMTP mocked to succeed, the composed message body contains ${INVITE_BASE_URL}/invite#<token> with the token ONLY in the fragment, never in a path segment. | config-service | onboarding api email backend
T16 | Task | Add authenticated invite management routes (POST/GET /invites, resend, revoke) | Invite-based user onboarding (Platform / Tenant) | Phase 3: API, email delivery and cutover | To Do | High | 3 | T9, T15 | services/config/routers/invites.py (new) | POST /invites, GET /invites (super_admin sees all; tenant-scoped actor's ?tenant_id= ignored/forced to JWT), POST /invites/{id}/resend, POST /invites/{id}/revoke, all under require_role("superadmin","admin"); the create/resend handlers call send_invite_email() after commit, non-fatal on failure. Done when: GET /invites?tenant_id=<other> as a tenant_admin returns only the actor's own tenant's invites (AC11); the same call as super_admin, unfiltered, returns invites across tenants; POST /invites returns 201 with email_sent: bool in the body; and with SMTP mocked to raise, POST /invites still returns 201 email_sent: false with the row status='pending' and resendable (AC12). | config-service | onboarding api email backend
T17 | Task | Add public GET/POST /invites/accept with X-Invite-Token header | Invite-based user onboarding (Platform / Tenant) | Phase 3: API, email delivery and cutover | To Do | High | 3 | T10, T15 | services/config/routers/invites.py | Token via X-Invite-Token header, no JWT dependency; returns only {email, tenant_name, role, status} on GET. Done when: a request with no Authorization header reaches both handlers (proving they bypass the console gate by construction); GET /invites/accept for a valid token returns no field naming any other account or tenant beyond the invitee's own; and accepting with a wrong/missing header/token structure 404s. | config-service | onboarding api email backend
T18 | Task | Add per-inviter fixed-window throttle for invite create/resend | Invite-based user onboarding (Platform / Tenant) | Phase 3: API, email delivery and cutover | To Do | High | 3 | T16 | services/config/app.py | In-process fixed-window throttle helper keyed on invited_by: 30 attempts/hour outcome-blind probe cap; 20 successful sends/hour across create+resend; 60s per-invite resend cooldown off last_sent_at. Done when: 30 consecutive create attempts that each 409 make the 31st 429 with Retry-After; a successful create attempt after 30 conflicts is ALSO 429 (proving outcome-blindness); 20 successful sends make the 21st 429 even with probe-counter room left; and two resends within 60s make the second 429 naming remaining seconds. | config-service | onboarding api email backend
T19 | Task | Add accept-route IP throttle, mount invites router, delete POST /users | Invite-based user onboarding (Platform / Tenant) | Phase 3: API, email delivery and cutover | To Do | High | 3 | T16, T17, T18 | services/config/app.py, services/config/routers/users.py | IP throttle keyed on request.client.host (NEVER X-Forwarded-For), 10/minute and 50/hour across GET+POST, plus the one-line comment documenting the trusted-proxy caveat; wire app.include_router(invites.router); and, now that the new path is reachable, delete POST /users (temp-password path). Done when: the 11th accept request from one IP in a minute is 429, byte-identical for a valid and an invalid token; a forged X-Forwarded-For header does not move the request into a different bucket than an identical request without it; POST /invites and POST /invites/accept are reachable end-to-end through the app; POST /users returns 404/405; and existing test_users.py cases for the deleted route are removed with the remaining suite passing — leaving a tenant able to onboard a user via invite at every point after this task, with no gap where neither path works. | config-service | onboarding api email backend
T20 | Task | Add Invite/User types and invite API client functions | Invite-based user onboarding (Platform / Tenant) | Phase 4: Admin UI | To Do | Medium | 3 | T16, T17 | admin-ui/lib/api.ts | Add Invite/User types and listUsers, listInvites, createInvite, resendInvite, revokeInvite, getInvite, acceptInvite. Done when: each function has a corresponding unit/integration test (or existing request()-pattern test) hitting a mocked endpoint and returning the typed shape, matching how other lib/api.ts functions are covered today. | admin-ui | onboarding frontend
T21 | Task | Build users + pending-invites management screen | Invite-based user onboarding (Platform / Tenant) | Phase 4: Admin UI | To Do | Medium | 5 | T20 | admin-ui/app/users/page.tsx (new), admin-ui/components/AppShell.tsx | Invite modal, resend disabled during cooldown, status column pending/expired/revoked/accepted. Done when: the nav item renders only for superadmin/admin roles; the page lists users and invites scoped to the viewer's tenant (or all tenants for super_admin, AC11); and an invite shown as email_sent: false still displays as pending with a working resend action (AC12). | admin-ui | onboarding frontend
T22 | Task | Build public invite accept page reading token from location.hash | Invite-based user onboarding (Platform / Tenant) | Phase 4: Admin UI | To Do | Medium | 3 | T20 | admin-ui/app/invite/page.tsx (new), admin-ui/components/AppShell.tsx | Sends the token as X-Invite-Token on GET/POST /invites/accept; treat /invite as a standalone unguarded route like /login. Done when: visiting /invite#<token> while unauthenticated does not bounce to /login; submitting a valid password calls POST /invites/accept with the token in the header and NEVER in the URL/query string; and an expired/revoked/already-used token renders its specific message (AC6, AC10). | admin-ui | onboarding frontend
T23 | Task | Add remaining invite integration coverage (soft-delete re-invite, normalization, audit rows) | Invite-based user onboarding (Platform / Tenant) | Phase 5: Test suite completion | To Do | Medium | 3 | T19, T22 | services/config/tests/test_invites.py, services/config/tests/test_users.py | Coverage not already produced as 'done when' checks above: soft-delete re-invite (invite -> accept -> soft-delete -> re-invite -> second live row, old row's password no longer authenticates); normalization (Bob@X.com invite resolves/blocks against bob@x.com account); and the audit-row-per-mutating-path assertion across create/resend/revoke/accept. Done when: all listed scenarios pass in pytest services/config/tests/. | config-service | onboarding testing

## Phase Notes
Phase | Sequencing constraint / note
Phase 1: Schema | Ordered, idempotent SQL steps — no migration tool. Follows the repo's existing idempotent-SQL convention (database/schema.sql, applied in order — see CURSOR.md), expressed as ordered ALTER/CREATE ... IF NOT EXISTS steps rather than a new migration tool. IMPORTANT: T1-T5 are reviewed and merged as ONE atomic schema.sql apply — they are not five independently deployable production states (T2 alone leaves users.email with no uniqueness guard at all until T4 lands). They are separate tasks only so each step is reviewable and individually re-runnable/idempotent within that single apply.
Phase 2: Backend core (identity, permissions, tokens) | Completing this phase must not remove or break any existing capability — no route is deleted here; POST /users stays reachable until its invite-based replacement is live (Phase 3).
Phase 3: API, email delivery and cutover | Email delivery is built here, BEFORE the routers that need it, so the router's own 'done when' (email_sent: bool) is satisfiable the moment this phase lands — not dependent on a later phase. POST /users is deleted at the END of this phase, once POST /invites + accept are mounted and reachable, so the system is never left without any account-creation path.
Phase 4: Admin UI | Frontend: API client, management screen, public accept page.
Phase 5: Test suite completion | Remaining integration coverage not already produced as 'done when' checks in earlier phases.

## Import Guide
Field | Value
Source | .sdlc/user-onboarding-hierarchy/03-tasks.md (generated verbatim — summaries condensed, 'done when' text preserved in the Description column)
Totals | 1 Epic + 23 Tasks. Done: 5 (T1-T5, Phase 1). Remaining: 18 (T6-T23). Story points total: 62 (remaining: 51).
How to import | Jira: Settings > System > External System Import > CSV. Save this sheet as CSV first (Jira's importer takes CSV, not .xlsx). Map columns on the field-mapping screen.
Field mapping | Summary -> Summary; Issue Type -> Issue Type; Description / Acceptance Criteria -> Description; Priority -> Priority; Story Points -> Story Points; Labels -> Labels (space-separated = multiple labels); Components -> Components; Epic Link -> Epic Link; Status -> Status (needs a matching workflow status, else leave unmapped and set later).
Task ID / Depends On | 'Task ID' and 'Depends On' are the T-numbers from the source doc, kept for traceability. Jira cannot create issue links on import from these — either map Task ID to a custom field, or create the 'blocks/is blocked by' links manually after import using the Depends On column.
Import the Epic first | Import the Epic row on its own first, or Epic Link on the task rows will not resolve. Alternative: import everything, then bulk-set the Epic.
Ordering caveat | Phase 1 (T1-T5) is already Done and ships as ONE atomic schema.sql apply, not five deployable states — see the Phase Notes sheet before splitting those into separate PRs or sprints.
AC references | AC2/AC3/AC4/AC6/AC10/AC11/AC12 in the Description column refer to acceptance criteria in .sdlc/user-onboarding-hierarchy/01-prd.md. 'lesson 3/5/9' refer to review lessons captured during the SDLC run.